## Sheet1
El Paso Bus Network Analysis - Project Management Plan Charlie Huemmler, Yingxue Ou, Jack Rummler |  |  |  | January |  |  | February |  |  |  | March |  |  |  | April
|  |  |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15
MAJOR TASK | MINOR TASK | ASSIGNED TO | PROGRESS | 1/15 - 1/21 | 1/22 - 1/28 | 1/29 - 2/4 | 2/5 - 2/11 | 2/12 - 2/18 | 2/19 - 2/25 | 2/26 - 3/4 | 3/5 - 3/11 | 3/12 - 3/18 | 3/19 - 3/25 | 3/26 - 4/1 | 4/2 - 4/8 | 4/9 - 4/15 | 4/16 - 4/22 | 4/23 - 4/29 | 4/30 -
Preliminary Tasks | Define Use Case | All | Complete | bar: 1899-12-31
| Data Wrangling | All | IP | bar: 1899-12-31 to 1900-01-02
| Basic Wireframing |  | Need | bar: 1900-01-02
Data Analytics | Data Wrangling | All | Need | bar: 1900-01-02
| Exploratory Analaysis | All | Need | bar: 1900-01-02 to 1900-01-05
| Feature Engineering | All | Need | bar: 1900-01-03 to 1900-01-05
Modeling | Model Strategization | All | Need | bar: 1900-01-04 to 1900-01-05
| Model Development | All | Need | bar: 1900-01-05 to 1900-01-13
App and Wireframe | App Development | Yingxue | Need | bar: 1900-01-05 to 1900-01-13
| App Finalization | Yingxue | Need | bar: 1900-01-13 to 1900-01-14
Markdown | Markdown Finalization | Charlie | Need | bar: 1900-01-13 to 1900-01-14
Finalization | Finalize for Studio | All | bar: 1900-01-14 to 1900-01-15
[5 empty] | PM Plan |  |  |  | Pres #1 |  |  |  |  | Pres #2 |  |  |  | Final Pres
[9 empty] | Markdown |  |  |  |  | Markdown